## Slide 1: Software Governance GE Capital International
EARL Implementation – all software audit – EMRG France
Jan 30, 2014
For discussion with
EMRG France SGLs

## Slide 2
Software Governance Mission Statement
To mitigate risk of license
non-compliance while optimizing software investment.
Notes: Software Governance is an interdependent series of components, owned by different organizations.
Pillar identifies a key component of the software governance process.
Description describes the main purpose of the pillar.
Tool identifies if an IT solution exists for that pillar.
Software Request & Licensing is a tool to facilitate approval routing for software requests and at the same time, also tracks all approved/purchased software over the lifecycle of that asset.
Application Depot is the standard tool used to delivery software to a pc/laptop. Other methods do exist for installation on a server, and other tools like the Engineering Software Store also exist for delivery/use of approved software.
But, no matter how the software is delivered, all 3rd party software is expected to have a record in SRL.
The last pillar represents reconciliation … which is the main reason all the other pillars exist. We must be able to prove compliant use of 3rd party software. This pillar pulls all the inputs together to determine.

## Slide 3: Business Go live plan for EARL
Getting access to
Procurement
Full Client
Software
Audit
Develop
Processes
Educate
Institutionalize
Communicate
EARL Development, testing, integration
Embed SW Asset Management into the normal BAU Operations.
Finance and business Buy in essential
Full Clients SW Baseline and reconciliation.
Gap Remediation
Measure
Monitor
To helpdesk, SGL, and end users, all actors
Monitor issues, address challenges, close all activities
Repeatable Process on Each Business

## Slide 4: Objectives, Process, Plan

## Slide 5
Activity description
This is…
This is a ALL Software audit activity, executed by GE Capital HQ in order to baseline the data for upload onto EARL and have minimum gaps
High Level Remediation Plan – Details on Slide 9
  Remove the product if not necessary
  If the product is required then
    Find the POE (Proof of Entitlement) and get it uploaded into EARL
This is not…
This is not a Vendor audit. The vendor is not involved.
** PLEASE DO NOT CONTACT THE VENDOR FOR ANY PURCHASE OR ENQUIRIES – REACH OUT TO US **

## Slide 6
In-scope /Out-of-scope
All desktop SW for which biz needs to locally purchase licenses
Out of scope
All SW titles for which biz is globally licensed e.g. webex connect, outlook
Freeware/Open source
Macs, servers
In-scope

## Slide 7: Capital EMRG France Recon Summary
# | Business | In Compliance | Out of Compliance | Financial Exposure
1 | Oracle Corporation | 0 | 54 | $4,270.00
2 | IBM Corporation | 0 | 29 | $0.00
3 | Microsoft Corporation | 31 | 26 | $14,479.98
4 | ReadSoft | 0 | 18 | $0.00
5 | Ascential Software | 0 | 13 | $0.00
6 | IDM Computer Solutions | 0 | 11 | $703.12
7 | Adobe Systems Incorporated | 7 | 9 | $1,736.28
8 | Patrick M. Kolla | 0 | 7 | $97.93
9 | SAS Institute Inc | 0 | 7 | $5,698.00
10 | Vmware | 0 | 7 | $0.00
11 | Wave Systems Corp. | 0 | 7 | $0.00
12 | CA | 0 | 4 | $0.00
13 | RARSoft | 0 | 4 | $100.24
14 | JD Stuart Ltd | 0 | 3 | $1.770.00
15 | WinZip Computing | 0 | 3 | $89.85
16 | ACL Services Ltd. | 0 | 2 | $0.00
17 | NTP Software | 0 | 2 | $0.00
18 | HTMLKit.com | 0 | 1 | $59.00
19 | Hummingbird Ltd | 0 | 1 | $499.52
20 | Ontrack Data Recovery, Inc. | 0 | 1 | $149.00
21 | QLogic Corporation | 0 | 1 | $0.00
22 | Splunk Inc. | 0 | 1 | $0.00
23 | Sysinternals | 0 | 1 | $0.00
24 | Attachmate | 2 | 0 | $0.00
 | Grand Total | 40 | 212 | $29,652.92

## Slide 8
Milestones
N° | Steps | Who | Start Date | Deadline | Main tasks | Duration
1 | Business engagement | Cap Intl HQ & Business | W1 (27/1) | W1 (27/1) | EARL Kick off Sharing ALL SW audit report to business | Week 1
2 | POE upload/Uninstall/ Purchase | Business | W1 (27/1) | W12 (28/4) | Biz targets 4 out of 24 sw titles every 2 weeks to complete remediation In each 2-week cycle: a) Biz uploads existing POE onto EARL for each sw b) If POE not available, biz uninstalls/ purchases c) Biz confirms Audit team that remediation done d) Audit team reviews the remediation e) If gaps present, business to remediate till zero gaps. Goto (a) f) If no gaps, Audit team sends closure request to GECC for the particular sw | Week 1 - Week 12
3 | Continuous remediation review | Cap Intl HQ | W2 (3/2) | W12 (28/4) | Audit Team performs recon every 2 weeks for each target sw If gaps present, business to remediate till zero gaps | Week 2 - Week 12
4 | Capital HQ review for closure | Cap Intl HQ, Capital HQ & Business | W2 (3/2) | W12 (28/4) | GECC to perform final review before closure for each sw title This will constitute as baseline data for upload onto Earl | Week 2 - Week 12
Wk1(27/1)
28/4
1
Wk2
End
2
3
* Date Format dd /mm/ yyyy
4

## Slide 9: Execution plan
Capital HQ runs audit
Sends report to Cap
Intl HQ
Cap Intl HQ engage
bizs and drive
the plan
Review GAP;
Confirm Scope / Assets
What is a valid POE? Ask “Sarita”
Capital HQ compared your ITAM with EARL; Software assets in ITAM not in EARL considered as potential gaps
Capital Intl Audit Services Team – SPOC for the Audit Cycle
For these entitlements not found, remove the sw if not needed
Get all the invoices uploaded into EARL;
How to upload into EARL? Sarita will show you process.
Cap Intl Audit Services Team will monitor your gap status and, when we think you are compliant we will ask GECC HQ to confirm
Repeatable Process on Each Business
Capital HQ
re-audits and
closes audit
GECC HQ to re audit your environment and validate that all products in scope are justified in EARL;
GECC HQ raises a formal closure.
If not all gaps are closed, go back
Remediation
confirmed?
Collect POEs/
Upload onto EARL/ Purchase
Remove unused SW

## Slide 10
What is a valid POE?
Records from software suppliers detailing product, version and quantity
(vendor consumption reports) + PO/Invoice number included in the report
License agreement paper with quantity purchased detailing product,
version and quantity + *Proof of Purchase (depending on the agreement)
Shrink wrapped box with the media/license included
GE issued and approved Purchase Order detailing product, version, and
quantity + matching invoice + other Finance documentation confirming that
payment has been settled in full
P card receipt detailing product, version and quantity
Documentation of license transfer via an acquisition
*Proof of Purchase : GE/Vendor purchase order + paid invoice + Other Finance
documentation confirming that payment has been settled in full

## Slide 11
Remediation, Recommendations
Look for entitlements lying with your business and not uploaded onto EARL. For entitlements not present, remove the unused software
We must respond diligently in the expected timeframes, the levels of flexibility will be short and based on approved exceptions
If you don’t find the proof of entitlement for a product, don’t waste your time trying to find it beyond acceptable efforts and perform remediation.
Speed up the procurement process, push for the PO to be approved and the invoice to be sent to you by the vendor, as otherwise will take weeks to happen.
As soon as you get the invoice, upload it into EARL. Don’t wait.

## Slide 12
Keys for success and Risks
Keys for success
Diligence, act quickly.
Rigor, remediate all the potential gaps.
Management Support, you may need to purchase something, engage management on this activity so they know a potential unexpected cost.
Talk, communicate. Don’t wait for emails, communication issues are the biggest issues we had so far in previous rounds.
Risks
Lack of historical focus in Software Governance may end up in lack of engagement/prioritization of the project, requiring cultural change and strong Sr. Management support. The game has changed now.

## Slide 13: Annex Why The Audit is Happening
A GE Wide initiative
Market trend.
Increased Regulatory control.

## Slide 14: Extract frm Martha Poulter All IT Pitch
Consistent, Global Processes
IT Risk Management
IT Security Services
IT Policy Coordination
Software License Compliance
IT Investment & Program Management
Federal Reserve Bank
“Enhanced Continuous Monitoring”
5 HQ IT reviews in 7 months
  IT Governance
  IT Security
  Project management /SDLC
  Vendor management
  DR / BCP
Field visits planned
  Poland end of June
  Japan early July
Theme
Consistent & appropriate oversight
Internal Audit
166 IT Audits planned for 2012
  Don’t get stuck on ratings
  Focus on findings
Organization
Environment

## Slide 15: Remediation Strategy
Identify Remediation Plan
30 Day Remediation Period – Notify CIO
Executes Purchase or Provides Entitlements
Reports Progress
Gaps? – Escalate to CIO
Capital HQ Purchases
Chargeback to Business
SW Gov Team
Business &
SW Gov Team
Business
SW Gov Team
SW Gov Team
Finance
* Tactical Solution Only
Remediation Period Expires
Generic High Level Process

## Slide 16
2013/14 SAM Stack
Aspera
EARL
UAPM Inventory
Ad hoc Processes
SW Dashboard
SW Dashboard
Rationalized: SW Inventory, Realtime Dashboard, Integrated SW Lifecycle processes, best in class market standard. All Software in Scope 2014/2015
Basic: SW Inventory, Monthly partial dashboard, Ad hoc SW Lifecycle processes. Now.
Standardized: SW Inventory, Integrated SW lifecycle processes, monthly top 10 dashboard.